## Sheet1
Project name | EXAM APP | Tester/ Name | MD. RAYHAN ALI
Project URL |  | Dev. Name | ABU UBAIDA
Credentials(Login) | ID: PASS: | QA Status | PASSED/FAILDE/IGNORE/REJECT/SUGEST
Product Owner | TEXON | DEV. STATUS | FIXED/NOT FIXED/IGNORE/PANDING
Created On | 2024-12-03
Feature Name | MOBILE APPLICATION
SL# OR SCENARIO ID | REPRODUCED STEP/PAGE NAME/FEATURE NAME | ISSUE DESCRIPTION | ATTACHMENTS/SCREENSHOT | DEV. STATUS | QA STATUS | ISSUE LOG DATE | LAST RETEST DATE | ANY COMMENTS | RESPONSIBLE
1 | Open Examtice app >then click news filed > then show chat icon like whatsapp | Chat option not working | https://prnt.sc/mcdNzqzMeffm | IGNORE | IGNORE | 2024-03-13 | 2024-03-14 | Web Related
2 | Open Examtice app >then click Eshop option> then click Buy Now>then click Subscribe | Navigation Eshop option after clicking Buy Now ,, then clicking subscribe option its not working | https://prnt.sc/kOn1DqmqjcFp | FIXED | PASSED | 2024-03-13 | 2024-03-14
3 | Open Examtice app >then click forum filed > then click Create New Thread | After clicking Create New Thread ,,,, create topic not working | https://prnt.sc/GJP9aOBbf0sv | FIXED | PASSED | 2024-03-13 | 2024-03-14 | Need to approve from backend
4 | Open Examtice app >then click forum filed > then click Public Topics >then click titile > then goto topics details page show a chatbox | topic Details page chatbox not working | https://prnt.sc/W5HJhVJ5svAa | FIXED | PASSED | 2024-03-13 | 2024-03-14
5 | Open Examtice app >then click notification icon | When Read All notification its not updated | https://prnt.sc/8yYNdmHpFarr | FIXED | PASSED | 2024-03-13 | 2024-03-14
6 | Open Examtice app >then click profile in the navigationbar | Reset Profile not working | https://prnt.sc/tv-W_ZxVrGz0 | FIXED | FAILED | 2024-03-13 | 2024-03-14
7 | Open Examtice app >then click Support then Create New Ticket> then click the created ticket> then show comments option | Comments option ,,,"write your message" viewing not good | https://prnt.sc/sRLugowTmmli | FIXED | PASSED | 2024-03-13 | 2024-03-14