## Rayhan
| QA Report From Client: | Konnect_MobileApp_Edits
Konnect Daily Progress
Admin Panel
Sl No | Title | Description | SS link | Problem URL |  | Dev Status | QA Status
1 | Notification Icon cannot working Properly | When View All notification Its not working | 3.png 3...png | https://konnect.texonltd.com/users/notification/app/social/notifications.html |  | Done
2 | Change password doesnot work show a message | Show this message You are not authorized to access this page. | 4.png | https://konnect.texonltd.com/users/change_password/ |  | Done | Passed
3 | App is too much slow not working properly | When check some categories app is not working | 5.jpg |  |  |  | Failed
4 | Login problem And Registration Problem | Some device can not login after Registration ..some device cannot create account | 6.jpg |  |  |  | Failed
5 | When login not show a message | When login if error passoward and email or phone not show any popup | 7.jpg |  |  |  | Failed
6 | User profile not working properly | user profie not working properly for example user occupation not working | 8.jpg |  |  |  | Failed
19-02-2024
Sl No | Issue Title | Description | Issue For | Responsible | Status | Screen Shot | Page URL
1 | Notification problem>>Always Shown an error after login or registration or refresh | Show a popup Message 'Error fetching notification data' | Apps | Done | Issues | https://prnt.sc/F7iGtKJeQiAQ
2 | User Account Settings Update Failed | User cannot update his account settings ,,,,show an Error message 'Account Settings update failed' | Apps | Done | Issues | https://prnt.sc/t27huGVNvRxO
3 | User Comments Add Picture or Image Icon not working | When an User Want to comments and add picture ..picture icon not working..Sometimes all comments not visible to others | Apps | Done | Issues | https://prnt.sc/hQ04vr-Az_ZA
4 | Event Details Page Chat option Not working | Event Chat ...Chatting with people not working | Apps | Done | Issues | https://prnt.sc/gDsdUocAKzu9
5 | Event Share Icon not working | Event Details page...event share icon not working | Apps | Done | Issues | https://prnt.sc/1N6Bscuv_3nd
6 | Otp not received in verified phone number | When Registration OTP not receive in verified phone number | Apps | Done | Issues | https://prnt.sc/0btyS3N8l_oP
7 | There are no time limit option in otp verification system | OTP verification Code page not show any kind of time log ... OTP expried time option needed | Apps | Done | Issues | https://prnt.sc/mrVqIbRJMMmB
8 |  |  | Apps |  | Issues
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30

## Shan
Title | Description | SS link | Problem URL | Dev Status | QA Status | Comments
User cannot create an account | After installing the mobile app, user should sign up for new account then use the app, but user cannot sign up | 1.jpg
Can not view report | In the dashboard of the admin panel, there is a text bottom of the chart which is not working after clicking | 2.png | https://konnect.texonltd.com/#! | Done | Passed
Not looking good | User can upload image but this field should proper understandable | 3.png | https://konnect.texonltd.com/users/create/
Not using dropdown option | Text type input field is used to find the country, dropdown with search option is not used. All the country names should display | 4.png | https://konnect.texonltd.com/users/create/
Not using date type input field | Text type input field is used to set date of birth. Date type input field should be used. | 5.png | https://konnect.texonltd.com/users/update/23/ | Done | Passed
Spelling is LogIn | Space should be used between LogIn text. It should be displayed either Log In or Login | 6.jpg
User cannot edit experience & education | Users can update their personal details but Experience and Education fields remain same | 7.png | https://konnect.texonltd.com/users/23/ | Done | Passed
Both are the same features | There are 2 buttons on each user's profile which are Edit and Setting buttons. Both button are used to update user's personal informaton. | 8.png | https://konnect.texonltd.com/users/4/ | Done | Passed
Wrong pop up message is displaying on Notification | After clicking Send button wrong pop up message is shown which is "Notification not send" but user gets notification. | 9.png | https://konnect.texonltd.com/users/notification/ | Done | Passed
Close button is not working on Notification page | Clicking the Close button, it should close the notification page and redirect to other page. But nothing happens. | 10.png | https://konnect.texonltd.com/users/notification/ | Done | Passed
No events are displayed at Recent Activity | After creating some new events, none are displayed there | 11.png | https://konnect.texonltd.com/ | Done | Passed
Spelling mistake (Upcomimg) | Spelling should be Upcoming instead of Upcomimg and no events are shown after adding new one | 12.png | https://konnect.texonltd.com/ | Done | Passed
Copyright year is 2023 at the footer ber | It should be displayed 2024 for new updaed version | 13.png | https://konnect.texonltd.com/
Unable to upload image | Admin cannot upload images to user profiles | 14.png | https://konnect.texonltd.com/users/update/14/