## Rayhan
Sl No | Issue Title | Description | Issue For | Responsible | Status | Screen Shot | Page URL
1 | Book Management ,, Book page show all books option Cover filed text dropdown icon too closed | Cover and dropdown icon too colsed not showing good | Admin Panel | Uzzal | QA Proved | 1.png | https://library.texonltd.com/books/
2 | Book Management ,, Book page show all books option audio Is special filed text dropdown icon too closed | Not showing good | Admin Panel | Uzzal | QA Proved | 2.png | https://library.texonltd.com/books/
3 | Create Sections orden no placeholder name not right | Create sections order no placeholder text not right | Admin Panel | Uzzal | QA Proved | 3.png | https://library.texonltd.com/books/chaptercreate/
4 | Book Management ,, Book page show all books option audio field don't show any kind of status | Uploded Audio but cannot show any knid of status | Admin Panel | Uzzal | QA Proved | 4.png | https://library.texonltd.com/books/
5 | Stuff list not create | After full fill all field Create new stuff not added in stuff list | Admin Panel | Uzzal | QA Proved | 5.png | https://library.texonltd.com/stuffslist/
6 | Book Reader(user) Delete option not working | Book Reader(user) page Delete option not working can not delete a user | Admin Panel | Uzzal | QA Proved | 6.png | https://library.texonltd.com/userslist/
7 | Slider page Delete option not working | slider page Delete option not working can not delete a slider | Admin Panel | Uzzal | QA Proved | 7.png | https://library.texonltd.com/books/sliderlist/
8 | dark mode viewing not work properly | In dark mode some viewing show lighting | Admin Panel | Uzzal | QA Proved | 8.png | https://library.texonltd.com/books/sections_name/
9 | Login Page terms and condition not working | Login home page terms and condition not working | Admin Panel | Uzzal | QA Proved | 9.png | https://library.texonltd.com/accounts/login/#!
10 | Audio Player Some features not working | Audio Player features icon not woking properly .. for example speaker icon not working | User Website |  | QA Proved | 10.jpg
11 | Searchbar funtionality not working | Searchbar ..Recent corros icon and clean all not working | User Website |  | QA Proved | 11.jpg | dependency on backend
12 | Bookmark option not working | Bookmark icon not working | User Website |  | QA Proved | 12.jpg | dependency on backend
13 | when add a book in favorite list its not remove | when add a book in favorite list then unselect the book..... its not remove from my book list | User Website |  | QA Proved
2024-11-03
14 | Book Read Counting Not Upateded | After Reading a book Number of Reading option not updated | User Website |  | Issues | https://prnt.sc/0Lm2ij4i0Cln
15 | Note Option Not Working Properly | When creating a note and then clicking to locate that line, the original line position cannot be found. | User Website |  | Issues | https://prnt.sc/TISwZe5s4UgR
16 | All pdf page number same | Page number not updated for specific pdf | User Website |  | Issues | https://prnt.sc/slevz84BXFIJ
17 | Image overflow | Image viewing not good some image Overflowed in Right Side | User Website |  | Issues | https://prnt.sc/CvxMCCB2SrNV
|  |  | User Website |  | Issues
|  |  | User Website |  | Issues
|  |  | User Website |  | Issues
|  |  | User Website |  | Issues
|  |  | User Website |  | Issues
Issues
Issues
Issues

## Shan
Sl No | Issue Title | Description | Issue For | Responsible | Status | Screen Shot | Page URL
1 | User cannot register | Providing valid data user can't create a new account and an error message which is not easy to understand | User Website | Abu Ubaida | QA Proved | 1.jpeg | https://prnt.sc/F6AL2G4Lz0oT
2 | User cannot login | Providing email and password user can't log into a registered account and an error message is not understandable | User Website | Abu Ubaida | QA Proved | 2.jpeg
3 | OTP is not sending for forgot password | Clicking "Send OTP" button, an alert message is displayed which is not understandable | User Website | Abu Ubaida | QA Proved | 3.jpeg
4 | No contents are appeared for catagory | After opening the application, this page opens to select category but nothing is displayed | User Website | Abu Ubaida | QA Proved | 4.jpeg
5 | Next button is not working | In the same page, if user click "Next" button then it don't redirect to other page | User Website | Abu Ubaida | QA Proved | 5.jpeg
6 | Guest User option is not working | User cannot visit the app using Guest User option as a guest and nothing happends after clicking that button | User Website | Abu Ubaida | QA Proved | 6.jpeg
2024-02-13
7 | No toggle option for password shown/hide | In password field, password is hidden but toggle option can be set to show that the written password is correct or not. Otherwise, Admin may confuse. | Admin Panel |  | QA Proved | 7.png | https://library.texonltd.com/accounts/login/
8 | Only User Name is written on the label | Admin can use email to login in the system. So, both can be written on the label. "User Name" can be written like this "Username" (no space) | Admin Panel |  | QA Proved | 8.png | https://library.texonltd.com/accounts/login/
9 | Logo is not understandable | Into the dashboard, logo is not understanding in Night vision mode | Admin Panel |  | Issues | 9.png | https://library.texonltd.com/dashboard/
10 | Footer is not updated | Site name is not set at footer and year can be set 2024 (current year) | Admin Panel |  | QA Proved | 10.png | https://library.texonltd.com/dashboard/
11 | Notification is not working | After clicking a new notification, it did not redirect to any page. But it should redirect to specific page in Admin panel | Admin Panel |  | QA Proved | 11.png | https://library.texonltd.com/dashboard/#
12 | Not marking notifications | Clicking the button notifications are not marked as read. Not understanding. | Admin Panel |  | QA Proved | 12.png | https://library.texonltd.com/dashboard/#
2024-02-15
13 | Notification Bar | Dot sign remains on the icon after deleting all existing notification | Admin Panel |  | QA Proved | 13.png | https://library.texonltd.com/dashboard/
14 | Which type of users | Not understandable that the users are staffs or book readers. It can be modified by showing them separately. | Admin Panel |  | QA Proved | 14.png | https://library.texonltd.com/stuffslist/
15 | Not redirects to staff list page | When a new notification appears it should redirect to staff list after clicking | Admin Panel |  | Issues | 15.png | https://library.texonltd.com/dashboard/
16 | No need Audio column |  | Admin Panel |  | QA Proved | 16.png | https://library.texonltd.com/books/
17 | Need to swap | After adding chapter, the values swap between "Chapter No." and "Word of page" | Admin Panel |  | QA Proved | 17.png | https://library.texonltd.com/books/create/
18 | Cross button doesn't work | It is not canceling the pop up after clicking the cross button | Admin Panel |  | QA Proved | 18.png | https://library.texonltd.com/books/create/
2024-02-18
19 | User not adding in stafflist | Got notification about creating user but that User is not being added in staff list | Admin Panel |  | QA Proved | 19.png | https://library.texonltd.com/stuffslist/