## Sheet1
Project name | ডিজিটাল সেবা রেজিস্ট্রার | Tester Name | RAFIUL SHAN
Project URL |  | Dev. Name | Momen Tohin
Credentials(Login) | MOBILE NUMBER: 01743128802 PASSWORD: admin | QA Status | PASSED/FAILDE/IGNORE/REJECT/SUGEST
Product Owner | TEXON SOFTWARE SOLUTION | DEV. STATUS | FIXED/NOT FIXED/IGNORE/ PANDING
Created On | 2024-03-13
Feature Name | Website
SL# OR SCENARIO ID | REPRODUCED STEP/PAGE NAME/FEATURE NAME | ISSUE TITTLE | ISSUE DESCRIPTION | ATTACHMENTS/SCREENSHOT | DEV. STATUS | QA STATUS | ISSUE LOG DATE | LAST RE-TEST DATE | ANY COMMENTS | RESPONSIBLE | Link
1 | Registration page | Looks wired | Both Label and Placeholder for each field are displayed. Only one attribute Label / Placeholder can be set for better user experience | 1.png | PANDING | IGNORE | 2024-03-13 |  |  |  | https://dsr.texonltd.com/registration/
2 | Registration page | Not disappear dropdown option | After selecting কৃষি or কৃষি অর্থনীতি ও গ্রামীণ উন্নয়ন option, sub category option do not disappear. But, it should disappear cause there are no sub-categorues in কৃষি OR কৃষি অর্থনীতি ও গ্রামীণ উন্নয়ন | 2.png | FIXED | PASSED | 2024-03-13 |  |  |  | https://dsr.texonltd.com/registration/
3 | Login page | Validation is not applied in Login | In mobile input field, it accepts any type of characters but it should takes only 11 digits and no validation message appear if input field is null | 3.png | FIXED | PASSED | 2024-03-13 |  |  |  | https://dsr.texonltd.com/login/
4 | Registration page | Validation is not applied in Registration | Same as Login issue | 4.png | FIXED | PASSED | 2024-03-13 |  |  |  | https://dsr.texonltd.com/registration/
5 | Login page | No Password visibility | There are no Toggle/ eye button to hide/show password | 5.png | PANDING | IGNORE | 2024-03-13 |  |  |  | https://dsr.texonltd.com/login/
6 | Login -> Dashboard | No success message appear | After a user successfully Logged into the dashboard, No success message appears that confirm user is valid | 6.png | FIXED | PASSED | 2024-03-13 |  |  |  | https://dsr.texonltd.com/
7 | Login -> Dashboard -> Profile | Can't edit user profile | Users can not edit their own profile. But, this feature should be implemented. | 7.png | FIXED | PASSED | 2024-03-13 |  |  |  | https://dsr.texonltd.com/profile/
8 | Dashboard -> দায়িত্বশীল কর্মকর্তা | Linked Text not working | After clicking ".... আরো দেখুন" other Responsible services are not shown. But more services should be shown. | 8.png | FIXED | PASSED | 2024-03-13 |  |  |  | https://dsr.texonltd.com/all-admin/
9 | Dashboard -> সেবা প্রতিবেদন | Button is not working | After clicking সেবা প্রতিবেদন button, it redirects to same page and nothing occurs, But it should redirect to other page for specific requirement. | 9.png | FIXED | PASSED | 2024-03-13 |  |  |  | https://dsr.texonltd.com/all-admin/#
10 | Dashboard -> সেবা গ্রহীতা | Sub category is not added | After adding অনুষদ and দপ্তর বা শাখা, it don't appear as a sub-category of অনুষদ | 10.png | FIXED | PASSED | 2024-03-13 |  |  |  | https://dsr.texonltd.com/all-user/
11 | Dashboard -> সেবা গ্রহীতা | Page is not responsive | Buttons break down | 11.png | FIXED | PASSED | 2024-03-14 |  |  |  | https://dsr.texonltd.com/all-user/