## Shan
Sl No | Section/Page | Issue Title | Description | Issue For | Responsible | Status | Screen Shot | Page URL
2024-02-20
1 | Home | Only 1 language | English language is set in Multilingual dropdown option. No need this option if only English is set. Or, other languages can be added. | User Website |  | Suggest | 1.png | https://quickstock.xyz/
2 | Home | UI issue | Text color is faded so it's hard to understand for user | User Website |  | Completed | 2.png | https://quickstock.xyz/
3 | Home | No space between 2 sections | There is no space so texts is so close to the box. So, space can be added | User Website |  | Completed | 3.png | https://quickstock.xyz/
4 | Home | Both buttons do the same work | Clicking the buttons redirect to Login page, but user can view only demo page after clicking "Start Free Trail" | User Website |  | Issues | 4.png | https://quickstock.xyz/
5 | Home | Spelling mistake | In the button, there is "Trail" instead of Trial | User Website |  | Issues | 5.png | https://quickstock.xyz/
6 | Home | Spelling mistake | In the text, there is "Shopes" instead of Shops | User Website |  | Issues | 6.png | https://quickstock.xyz/
7 | Home | No images are added | There are blank spaces inside each section so images can be added | User Website |  | Issues | 7.png | https://quickstock.xyz/
8 | Home | Text issue | No opening inverted comma and texts are so much. | User Website |  | Issues | 8.png | https://quickstock.xyz/
9 | Home | Blank section | Nothings are added in the indicated section into the footer | User Website |  | Issues | 9.png | https://quickstock.xyz/
10 | Home | Logo can be modified | In the footer, logo is not matched so it can be modified for better user experience | User Website |  | Suggest | 10.png | https://quickstock.xyz/
11 | Home | Social icons are not working | In the footer, indicated icons do not redirect to social pages | User Website |  | Issues | 11.png | https://quickstock.xyz/
12 | Home | Footer can be modified | Footer is not matched with entire webpages. So, background color can be changed or image can added | User Website |  | Suggest | 12.png | https://quickstock.xyz/
13 | Home / Features | Contents are not specific | Contents are not properly written for each sector. And, clicking the item box should redirect to that blog page for more details | User Website |  | Issues | 13.png | https://quickstock.xyz/features
14 | Home / Features | Worg contents | Same as 13 | User Website |  | Issues | 14.png | https://quickstock.xyz/features
15 | Home / Features | Worg contents | Same as 13 | User Website |  | Issues | 15.png | https://quickstock.xyz/features
16 | Home / Register | Spelling mistake | In the text, there is "Passwrod" instead of Password | User Website |  | Issues | 16.png | https://quickstock.xyz/register
17 | Home | Text modification | "It's built with Vue.js and Laravel framework." This text can me written instead of indicated text. | User Website |  | Suggest | 17.png | https://quickstock.xyz/
18 | Home | No space between 2 words | Need to give a space in the indicated text | User Website |  | Issues | 18.png | https://quickstock.xyz/
19 | Mobile view | Not responsible | Panel is not responsible for small screen or in mobile | Admin Panel |  | Issues | 19.png | https://quickstock.xyz/
20 | Dashboard | Logo is shrunk | Lago can be modified by doing it more expand | Admin Panel |  | Issues | 20.png | https://quickstock.xyz/admin/dashboard
21 | Dashboard -> Product Manager -> Variations | Text not complete | User can not understand the dropdown option when search for any variants | Admin Panel |  | Issues | 21.png | https://quickstock.xyz/admin/variations
22 | Dashboard -> Product Manager -> Variations | No need to add laborer | To add a product in the system, no need to add laborer's name and also all the text should be written in English | Admin Panel |  | Issues | 22.png | https://quickstock.xyz/admin/products
23 | Dashboard -> Sales -> Sales | Input field is short | Place holder gets cut so admin can not read proper text for searching | Admin Panel |  | Issues | 23.png | https://quickstock.xyz/admin/stock/sales
24 | Dashboard -> Sales -> Payment In | Input fields are short | same as 23 | Admin Panel |  | Issues | 24.png | https://quickstock.xyz/admin/payment/in
25 | Dashboard -> Sales -> Quotation / Estimate | Input fields are short | same as 24 | Admin Panel |  | Issues | 25.png | https://quickstock.xyz/admin/stock/quotations
26 | Dashboard -> Sales -> Payment In | Buttons do not work | Clicking download buttons, it do not download payment slip but it should be downloaded | Admin Panel |  | Issues | 26.png | https://quickstock.xyz/admin/payment/in
2024-02-22
27 | Dashboard -> Settings -> Email Settings | Overlapping | Texts are overlapping so distance between the columns can be increased | Admin Panel |  | Issues | 27.png | https://quickstock.xyz/admin/settings/email
28 | Dashboard -> Online Orders | Short input field | Input field for adding URL is short but the size of the field can be increase | Admin Panel |  | Suggest | 28.png | https://quickstock.xyz/admin/stock/online-orders
29
30